## Budget by Group 9
PHASES | BLOCKS | STAGE | Avg Monthly | Avg Total | 22 months
Phase1 Research |  |  |  |  | 6 months
| Analysis, Design, Expert Collaboration |  |  |  | 2 months
|  | Research and data analysis for targeting regions and market scope with QA/QC | 80000 | 160000
|  | Collaborate with knowledge partners like universities, research organizations, foundations | 100000 | 200000
| Date | WAR/DAR |  |  | 50% |  |  | Total%
| Date | WAR/DAR |  |  | 23% |  |  | Total%
| Discussion (Chai Pe Charcha) |  |  |  |  | 1 month
|  | Talks with stakeholders (Local Farmers) | 12000 | 12000
People survey via meeting for confidence
|  | Contractual agreement design | 30000 | 30000
|  | Task - Creating Farmers Producers Organization | 25000 | 25000
| Expert Survey | [5 empty] | 3 months
|  | Survey the farmlands and understand local situation and first risk assessment | 100000 | 300000
Assess suitability and crop production
Planning for farming infrastructure (Contractors)
Design area infrastructure
Phase2 Planning | [8 empty] | 6 months
| Budgeting and Raising Funds | [7 empty] | 4 months
Budget Analysis (Max time)
|  | Strategize and Develop a GTM framework for investors and government bodies | 100000 | 400000
|  | Initial capital raising, govt investor contract design | 17000 | 17000
(Sources of Money – capital grant, no security loan)
| Tech | [8 empty] | 2 months
|  | Develop Web tool and App (Features like AR, RS prediction AI, demand planning) | 550000 | 550000
| Training | [9 empty] | 1 month
|  | Knowledge transfer to on-ground partners (Labor) | 6000 | 120000
|  | Second risk assessment | 100000 | 100000
|  | Second round capital raising (bank loans on behalf of farmers) | 100000 | 100000
Phase3 Implementation | [9 empty] | 12 months
| Implementation | [8 empty] | 5 months
|  | Prioritization of backlog – task assignment as large project based on funds (salaries) | 225000 | 225000
|  | Procurement of raw materials | 2075000 | 2075000
|  | Energy costs | 700000 | 700000
|  | Execution | 4000 | 24000
| Vendor Collaboration and Development | [8 empty] | 6 months
|  | Connect with large retailers and distribution partners, local bazar (Mandis) | 280000 | 280000
|  | Spread awareness and organic marketing activities | 30000 | 30000
| Produce and Process | [10 empty] | 8 months
|  | Sow and Breed the specific crops, poultry, fishes depending on the seasonality and other | 600000 | 600000
|  | Labor | 5000 | 70000
|  | Monitor and Control - QA/QC | 150000 | 150000
|  | Overhead Costs | 850000 | 850000
7018000
All figures in INR